## Timeline
Cucuyagua SCD |  |  | Timeline 10.20.2023
Qty | Unit | Decription |  | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
|  |  | 0 | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Jan
Receipt of funds
Community Development
1 | each | Leadership School for Women, Doctrine for Leaders, Healthy Homes and Schools, Source of Living Water
1 | each | World Vision Phase II Workshops to train the trainers on Risk Prevention Plans, Intertwining, Youth Ready and Nurturing Care
3 | each | Community inclusion activities
12 | each | Training sessions on community empowerment
6 | each | Training sessions for the social and economic empowerment of women
6 | each | Community leadership training (only for leaders and boards)
12 | each | Workshops on "Youth Ready" methodology for young people from the community
14 | each | Education in values for families (3 training sessions for each group of 6 families, 2 groups per visit)
21 | each | Workshops on "Nurturing Care" for parents and caregivers (include modules on positive discipline, the importance of early education, and healthy habits)
3 | each | Social promoter salary (3 years)
Income Generation Activities
1 | each | Market and economic opportunity analysis / Design and socialization
4 | each | Training sessions for the creation of rotating savings groups
3 | each | Training sessions on basic financial principles
3 | each | Creating my own business module
1 | each | IGA project implementation training
1 | each | IGA project implementation
Infrastructure
1 | each | Designs - civil and architectural drawings for infrastructure projects that will be presented in phase II
1 | each | Land leveling and road opening
1 | each | Lot distribution and marking in the field with topographic surveying
1 | each | Topopgraphic supervisión. On-site topography for supervising the proper execution of land leveling and marking works - 3 months
1 | each | Sewage system and wastewater treatment plant
1 | each | Water project. Includes 5,000-gallon water tank, conduction line and distribution line to each houses
1 | each | Water purification system (model SPR -RO -500). Includes operation and maintenance trainings to the community water commeetee and spare part kits
1 | each | Water purification system enclosure
1 | each | Concrete rain water drainage ditches
1 | each | Community electric system (Includes concrete poles with lamps and electric transformers)
1 | each | Community center with, drop-down ceiling and airconditioning
52 | each | Housing units - construction of two - bedroom houses with water and sanitation (Includes fixtures and household furnishings)
156 | each | Planting fruit and shade trees for each house (3 each)
1 | each | Feeding center construction
1 | each | Feeding center 1 year sustainability
54 | each | Supervision visits of civil engineer to construction site
1 | each | Contingency funds for emergency needs (not limited to natural disasters and risk mitigation measures)
Monitoring, Evaluation, Evaluation, Design, Accountability and Learning (MEDAL)
6 | each | Baseline and project evaluations

## legend & scenarios
Legend
Nothing planned
Planned project activities, not yet started
Expected completion month
Activity is in progress
Activity is fully completed
Activity timeline has been extended, and this is the expected completion month
Activity is delayed
3 | Current month
Example:
In the original timeline, an activity may appear as follows:
|  | PERCENT COMPLETE | Months
Activity |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | Interpretation:
1.1 Construction of 30 houses with water & sanitation | [10 empty] | Houses are meant to be finished within a period of 4 months, starting at month 2 and ending in Month 5
This is what progress on that activity would look like over time:
| Scenario 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  | Interpretation:
We're in Month 1 and the activity is supposed to start in Month 2 and finish in Month 5 (No change to timeline)
| Scenario 2 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
The activity is delayed. We are currently in Month 2. The activity is expected to finish in Month 5 (No change to timeline)
| Scenario 3 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
The activity was delayed by one month, but it is now in progress, and we are currently in Month 3 (No change to timeline)
| Scenario 4 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Despite the activity being delayed by one month, we have now had two months of progress, and we are currently in Month 4 (No change to timeline)
| Scenario 5 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
Despite the activity being delayed by one month, we finished on time in Month 5, which we are currently in (No change to timeline)
| Scenario 6 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
The activity timeline was extended by one month, and is expected to finish in Month 6 instead of Month 5. We are currently in Month 6, and the activity is still in progress (Change to timeline)
| Scenario 7 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
The activity was expected to be completed in Month 5, but the expected month of completion is now Month 7, and we are currently in Month 4 (Change to timeline)
| Scenario 8 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
The activity was supposed to finish in Month 5, but the timeline was extended. We are in Month 6 and there is a delay. Timeline is now extended until Month 8. (Change to timeline) | bar: 2 to 8
| Scenario 9 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
The activity timeline was extended by one month to Month 6, which we are currently in, and the activity is now complete (Change to timeline) | bar: 2 to 6
| Scenario 10 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7
The activity timeline finished one month early, in Month 4 instead of Month 5. We are currently in Month 4. (Change to timeline) | bar: 2 to 5